## Sheet1
Risk ID | Affected Asset(s) | Threat | Vulnerability / Cause | Impact | Likelihood | Risk Score | Priority | Treatment | Proposed Control
R1 | A13, A14 | Phishing attack leading to credential theft and unauthorized access | Weak user awareness, insufficient email filtering, inconsistent MFA | 5 | 5 | 25 | Critical | Mitigate | MFA, phishing training, secure email gateway
R2 | A1, A2, A17 | Ransomware encrypts hospital systems and disrupts patient care | Weak enpoint security, weak segmentation, poor backup isolation | 5 | 4 | 20 | Critical | Mitigate | Segmentation, EDR, immutable backups, and patching
R3 | A3, A4, A5 | Malware or ransomware disrupts clinical subsystems (radiology, lab, pharmacy) | Legacy systems, weak patch management | 5 | 3 | 15 | High | Mitigate | Segmentation, regular patching
R4 | A13 | Active Directory compromise, leading to full system takeover | Weak privileged access control, excessive admin rights | 5 | 3 | 15 | High | Mitigate | MFA for admins, least privilege access rights, logging
R5 | A1 | Targeted ransomware or wiper malware causes HER outage | Lack of redundancy | 5 | 3 | 15 | High | Mitigate | Ensure high availability, Disaster recover plan
R6 | A6, A7 | SQL injection or authentication bypass compromises scheduling systems | Weak application security | 4 | 3 | 12 | Medium | Mitigate | Secure WAF, testing
R7 | A19-A22 | Exploitation of vulnerable medical device firmware | Legacy medical devices, weak patching, network exposure | 5 | 2 | 10 | Medium | Mitigate | Device segmentation, monitoring
R8 | A1, A2, A8 | Insider data exfiltration via privileged accounts | Excessive access rights, weak monitoring of user activity | 5 | 3 | 15 | High | Mitigate | Implementation of RBAC, logging, and access review
R9 | A15, A18 | Lateral movement via SMB&RDP after credential theft | Flat network architecture | 4 | 4 | 16 | High | Mitigate | Segmentation, zero trust
R10 | A18 | Unpatched endpoint vulnerabilities | Weak patch management | 4 | 4 | 16 | High | Mitigate | Implementation of patch management, vulnerability scanning
R11 | A14, A19, A10 | email compromise using spoofed domains or compromised accounts leading to fraud | Weak verification process | 5 | 3 | 15 | High | Mitigate | Implement MFA, DMARC, process controls
R12 | A23, A26, A27 | Physical intrusion or IoT/CCTV compromise enabling unauthorized system access | Weak authentication, outdated firmware, no netowrk isolation for IoT/CCTV devices | 5 | 3 | 15 | Medium | Mitigate | Segmentation, access cntrol
R13 | A10, A11 | Supply chain attack via malicious software update | Weak vendor controls | 5 | 2 | 10 | Medium | Mitigate | Vendor risk mitigation strategy
R14 | A1, A14 | DDoS attack disrupts HER or patient-facing services | No traffic filtering | 4 | 3 | 12 | Medium | Mitigate | DDoS protection
R15 | A1, A2, A8 | GDPR non-compliance due to poor logging or encryption | Weak governance | 5 | 3 | 15 | High | Mitigate | Policies, audits
R16 | A1, A4, A5 | Misconfiguration exposes or deletes critical data | Weak management control | 4 | 4 | 16 | High | Mitigate | Change controls, backups
R17 | A16 | Firewall misconfiguraion allows malicious traffic | Poor rule management | 4 | 3 | 12 | Medium | Mitigate | Review of firewall rules, monitoring
R18 | A29, A25 | Unauthorized access to helipad lighting via BMS disables landing lights | Weak IT segmentation, insecure remote access | 5 | 2 | 10 | Medium | Mitigate | Segmentation, access control, manual override
R19 | A12, A17, A23 | Backup system failure during disaster or ransomware incident | Incomplete backup testing, lack of offline backups | 5 | 2 | 10 | Medium | Mitigate | Regular testing of backup restoration
R20 | A10, A12, A14 | Cloud/SaaS account takeover via stolen credentials | Lack of MFA, weak identity protection, overprivileged accounts | 4 | 3 | 12 | Medium | Mitigate | MFA, conditional access, identity monitoring, least privilege